## Dashboard
Leave Forms Revamp — Frontend Leader Tracker
Development started 2026-07-21. Commitment: DEVELOPMENT complete by 2026-08-31 (end of August). Testing & documentation are AFTER development (dates TBD).
Backend Integration is listed separately — schedule depends on the backend partner. No separate login page (portal cookies/session). Days = weekdays only when both dates are set.
Last aligned to codebase: 2026-07-29 — all employee, approver/team, and admin screens now have real UI with mock data; 2 minor report sub-pages still placeholders; cookie/session and live API not wired yet.
Scoring for Progress % / Overall %: Completed = 100% ¦ In Progress = 50% ¦ Not Started / Blocked = 0% · Overall % = average of ALL task Progress % (not average of section %)
Overall % |  | Completed (=100%) |  | In Progress (=50%) |  | Not Started (=0%)
Section | Tasks | Completed | In Progress | Not Started | Blocked | Progress %
1. Project Setup
2. Core App Shell
3. Employee Features
4. Approver / Team Features
5. Admin Features
6. Backend Integration (TBD)
7. Testing (after development)
8. Documentation (after development)
Development progress (sections 1–5 only)

## Tentative Schedule
Tentative Schedule — Frontend development (to end of August 2026)
Started 2026-07-21. August commitment = DEVELOPMENT only (through 2026-08-31). Backend integration dates TBD. Testing & documentation after development.
Phase | Start Date | End Date | Days (weekdays) | Focus | Weekly Date
Phase 1 — Foundation (development) | 2026-07-21 | 2026-07-30 |  | Project setup, layout, menus, reusable UI.
Phase 2 — Employee features (development) | 2026-07-28 | 2026-08-13 |  | Dashboard, file leave, request details, history, edit, and cancel.
Phase 3 — Approver / team (development) | 2026-08-11 | 2026-08-21 |  | Approvals inbox, approve/reject, file for member, team calendar.
Phase 4 — Admin features (development) | 2026-08-18 | 2026-08-28 |  | Admin requests, conversion review, balances, logs, and reports.
Phase 5 — Development complete (commitment) | 2026-08-28 | 2026-08-31 |  | Frontend development screens targeted complete. End of August = development only.
After / alongside development (no fixed end dates yet)
Item | Notes
Backend integration (parallel / TBD) | Ongoing with backend partner — no fixed day count yet. Update when APIs and cookie/session are ready.
Testing (after development) | Planned to start on/after 2026-09-01. End date TBD.
Documentation (after development) | Planned to start on/after 2026-09-01. End date TBD.
Key milestones (development)
Milestone | Target Date | Weekly Date | Related section
App shell & menus ready (dev kickoff) | 2026-07-22 |  | 2. Core App Shell
Reusable UI + employee screens underway | 2026-07-31 |  | 2–3
Employee filing & history usable (UI) | 2026-08-13 |  | 3. Employee Features
Approver approve/reject usable (UI) | 2026-08-18 |  | 4. Approver / Team
Admin screens usable (UI) | 2026-08-28 |  | 5. Admin Features
Development complete (August commitment) | 2026-08-31 |  | Sections 1–5
Weekly checkpoints (Fridays) — development
Week ending (Friday) | What leaders should expect to see
2026-07-24 | Kickoff: layout/menus; align cookie/session & API approach with backend
2026-07-31 | Reusable UI started; employee screens beginning
2026-08-07 | Employee dashboard and file-leave UI in progress
2026-08-14 | Employee UI largely complete; approver screens started
2026-08-21 | Approver UI in place; admin screens underway
2026-08-28 | Admin UI in progress / wrapping up
2026-08-31 | Target: frontend DEVELOPMENT complete (not testing/docs)
Formulas:
Days (weekdays) = NETWORKDAYS([Start Date],[End Date])

## Progress Tracker
Section | Task | Start Date | End Date | Days (weekdays) | Status | Progress % | Weekly Date | Notes
1. Project Setup | Set up frontend project (React, TypeScript, styling tools) | 2026-07-21 | 2026-07-21 |  | Completed
1. Project Setup | Apply brand colors, fonts, and base page styles | 2026-07-21 | 2026-07-22 |  | Completed
1. Project Setup | Define page routes for Employee, Approver, and Admin areas | 2026-07-21 | 2026-07-22 |  | Completed
2. Core App Shell | Build main app layout (sidebar menu and top header) | 2026-07-21 | 2026-07-22 |  | Completed
2. Core App Shell | Show different menus based on user role (Employee / Approver / Admin) | 2026-07-21 | 2026-07-22 |  | Completed |  |  | Role-based sidebar works. Dev-only role preview remains until portal cookies/session are wired.
2. Core App Shell | Create reusable screen parts (buttons, forms, tables, status labels) | 2026-07-22 | 2026-07-29 |  | Completed |  |  | Built: StatusBadge, FilterSelect, Pagination, Button, Modal, ConfirmReasonModal, AttachmentPreviewModal, SuccessDialog, Skeleton, form fields, MonthYearPickerField, EmployeeMultiSelect, tableStyles, admin-specific components.
2. Core App Shell | Replace temporary placeholder pages with real screens | 2026-07-22 | 2026-07-29 |  | Completed |  |  | All employee, approver/team, and admin routes now have real page components. No PagePlaceholder routes remain (only 2 minor sub-reports still placeholders).
3. Employee Features | Employee dashboard: leave balances and recent requests | 2026-07-22 | 2026-07-22 |  | Completed |  |  | UI complete (balances, reserved credits, filters, pagination). Uses mock data until Backend Integration.
3. Employee Features | File leave request (dates, leave type, reason, attachment) | 2026-07-23 | 2026-07-23 |  | Completed |  |  | Apply Leave page is built with employee info, leave type/day type, date range, reason, attachment rules, duration preview, confirm modal, and success dialog. Uses mock submit until Backend Integration.
3. Employee Features | Show unpaid leave (LWOP) warning when credits are not enough | 2026-07-23 | 2026-07-23 |  | Completed |  |  | LWOP / remaining-balance warning is shown in filing forms using mock remaining-day logic.
3. Employee Features | Leave request details: status, approvals needed, and activity history | 2026-07-22 | 2026-07-22 |  | Completed |  |  | UI complete: leave info, approval progress/requirements, approver list, attachments, conversion view. Mock data; activity timeline not a separate log yet.
3. Employee Features | Activity log / leave history with filters | 2026-07-23 | 2026-07-23 |  | Completed |  |  | Activity Log page exists with filtering, sorting, pagination, and mock activity data.
3. Employee Features | Edit leave request (only while still waiting for first approval) | 2026-07-22 | 2026-08-13 |  | Completed |  |  | Edit Leave page exists with date/day-type/reason editing, weekday duration recalculation, lead-time validation, confirm modal, and rules from details page. Uses mock save until Backend Integration.
3. Employee Features | Cancel leave request (with required reason) | 2026-07-22 | 2026-08-13 |  | Completed |  |  | Cancel flow is present on details page with required-reason modal and success state. Uses mock action until Backend Integration.
3. Employee Features | Request vacation-to-sick leave conversion (upload medical certificate) | 2026-07-23 | 2026-07-23 |  | Completed |  |  | Conversion page exists with reason + medical certificate upload, eligibility rules, confirm modal, and mock submission.
4. Approver / Team Features | Approver inbox: list of leave requests waiting for action | 2026-07-23 | 2026-07-23 |  | Completed |  |  | Leave Approvals page exists with pending/all tabs, search, filters, sorting, pagination, and mock queue data.
4. Approver / Team Features | Approve or reject leave (reject requires remarks) | 2026-07-23 | 2026-07-23 |  | Completed |  |  | Review page supports approve/reject actions, required rejection reason, confirmation modals, and success dialogs. Uses mock actions until Backend Integration.
4. Approver / Team Features | Show clear approval progress (who still needs to act) | 2026-07-22 | 2026-08-18 |  | Completed |  |  | Approval progress bars, requirement checklist, and approver status tables are built on employee details and approver review pages.
4. Approver / Team Features | File leave on behalf of a team member | 2026-07-23 | 2026-07-23 |  | Completed |  |  | File Leave for Member page exists with member selection, leave form, LWOP warning, attachment rules, confirm modal, and mock submit.
4. Approver / Team Features | Team leave calendar and upcoming approved leaves | 2026-07-29 | 2026-07-29 |  | Completed |  |  | Team Leave Calendar page (month/week views, filters, leave chips) and Upcoming Approved Leaves page are both built with mock data.
5. Admin Features | Admin view of leave requests and request details | 2026-07-29 | 2026-07-29 |  | Completed |  |  | Admin Leave Requests list (pending/all tabs, filters, search, reminders) and detail/view/validate pages are all built with mock data.
5. Admin Features | Review vacation-to-sick leave conversion requests | 2026-07-29 | 2026-07-29 |  | Completed |  |  | Conversion review is handled via Admin Leave Validate page; conversion state visible on request detail/view pages.
5. Admin Features | Manage leave balances and credit distribution | 2026-07-29 | 2026-07-29 |  | Completed |  |  | Admin Leave Balances page with filters, adjust-credits modal, and full distribution flows (annual, newly-regularized, parental, contractual) are built with mock data.
5. Admin Features | Administrative logs | 2026-07-29 | 2026-07-29 |  | Completed |  |  | Admin Administrative Log page with search, filters, month-year picker, sorting, and pagination is built with mock data.
5. Admin Features | Leave reports for management review | 2026-07-29 | 2026-07-29 |  | In Progress |  |  | Monthly Attendance Report page built. Leave Monetization Candidates and Employees with LWOP sub-reports are still placeholders.
5. Admin Features | Support other leave types (emergency, maternity, etc.) in the screens | 2026-07-22 | 2026-07-29 |  | Completed |  |  | Emergency, PTB, Maternity/Paternity handled in employee/team filing and in admin screens. Monthly attendance report covers all leave categories including LWOP.
6. Backend Integration (TBD) | Connect frontend to backend API (base connection and shared data types) | 2026-07-23 |  |  | Not Started |  |  | Duration TBD — frontend and backend work separately. Update Start/End when schedule is known.
6. Backend Integration (TBD) | Use portal cookies / session to identify the user (no separate login page) | 2026-07-23 |  |  | Not Started |  |  | Duration TBD — frontend and backend work separately. Update Start/End when schedule is known. Agreed with backend: cookies/session — no login screen.
6. Backend Integration (TBD) | Connect employee leave screens to live API (file, history, cancel, edit) |  |  |  | Not Started |  |  | Duration TBD — frontend and backend work separately. Update Start/End when schedule is known.
6. Backend Integration (TBD) | Connect approver / team screens to live API (inbox, approve, reject) |  |  |  | Not Started |  |  | Duration TBD — frontend and backend work separately. Update Start/End when schedule is known.
6. Backend Integration (TBD) | Connect admin screens to live API (balances, conversion, reports) |  |  |  | Not Started |  |  | Duration TBD — frontend and backend work separately. Update Start/End when schedule is known.
6. Backend Integration (TBD) | Joint frontend–backend smoke check once APIs are available |  |  |  | Not Started |  |  | Duration TBD — frontend and backend work separately. Update Start/End when schedule is known.
7. Testing (after development) | Employee flow testing (file, edit, cancel, view history) | 2026-09-01 |  |  | Not Started |  |  | Starts after development. End of August commitment covers development only — dates TBD.
7. Testing (after development) | Approver flow testing (approve, reject, team views) | 2026-09-01 |  |  | Not Started |  |  | Starts after development. End of August commitment covers development only — dates TBD.
7. Testing (after development) | Admin flow testing (balances, conversion, reports) | 2026-09-01 |  |  | Not Started |  |  | Starts after development. End of August commitment covers development only — dates TBD.
7. Testing (after development) | Mobile / responsive check on common screens | 2026-09-01 |  |  | Not Started |  |  | Starts after development. End of August commitment covers development only — dates TBD.
7. Testing (after development) | Fix issues found during testing | 2026-09-01 |  |  | Not Started |  |  | Starts after development. End of August commitment covers development only — dates TBD.
8. Documentation (after development) | Finalize frontend guide for the team (FRONTEND.md) | 2026-09-01 |  |  | Not Started |  |  | Starts after development. End of August commitment covers development only — dates TBD.
8. Documentation (after development) | Prepare short demo / walkthrough notes for stakeholders | 2026-09-01 |  |  | Not Started |  |  | Starts after development. End of August commitment covers development only — dates TBD.
8. Documentation (after development) | Handover checklist (how to run, deploy, and who owns what) | 2026-09-01 |  |  | Not Started |  |  | Starts after development. End of August commitment covers development only — dates TBD.
Commitment: frontend DEVELOPMENT finished by end of August (weekdays = NETWORKDAYS). Backend Integration has TBD end dates (teams work separately — fill dates when known). Testing and Documentation start after development (from Sep 2026); end dates TBD. No login page — portal cookies/session with backend.
Formulas:
Days (weekdays) = IF(OR([Start Date]="",[End Date]=""),"",NETWORKDAYS([Start Date],[End Date]))

## How to use
How to use this workbook
August commitment
Only frontend DEVELOPMENT is committed to finish by end of August.
Testing and documentation come AFTER development (start ~1 Sep; end dates TBD).
Backend Integration is listed with TBD dates — teams work separately for now.
For leaders / managers
1. Dashboard — overall % and section progress (also see Development progress for sections 1–5).
2. Tentative Schedule — development phases through August; backend/testing/docs called out as TBD/after.
3. Progress Tracker — update Status here.
For the development team
1. Change Status on Progress Tracker (dropdown).
2. For Backend Integration / Testing / Documentation: fill Start and End dates when known.
3. Keyword for Cursor: Update the leader tracker from the code
Workdays
Days (weekdays) uses NETWORKDAYS when both Start and End are filled (Mon–Fri only).
Authentication
No login page. User identity via portal cookies/session with the backend partner.
Status meanings
Completed / In Progress / Not Started / Blocked
Scoring: Completed = 100%, In Progress = 50%, else 0%.
Related files
docs/FRONTEND.md